## Data
Project ID | Project Name | Region | City | Customer Type | Project Value (₹ Lakhs) | Start Date | Planned Completion | Actual Completion | Delay (Days) | Installation Stage | Status | Handover Status | Delay Status |  | Checking Duplicte | Blank Value
PRJ001 | Skyline Residency | Central Kerala | Kochi | Residential | 18 | 2026-01-02 | 2026-04-15 | 2026-04-12 | -3 | Handover | Completed | Completed | Early | 1 | 1 | 0 | A2 to A306
PRJ002 | Green Valley Apartments | Central Kerala | Kochi | Apartment | 24 | 2026-01-10 | 2026-05-25 | 2026-05-30 | 5 | Handover | Completed | Completed | Delayed |  | 1 | 1 | A2 to A307
PRJ003 | Orchid Hospital | South Kerala | Trivandrum | Hospital | 42 | 2026-01-18 | 2026-06-30 | 2026-06-28 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ004 | Metro Business Park | Central Kerala | Kochi | Office | 65 | 2026-02-01 | 2026-07-30 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ005 | Grand Palace Hotel | Central Kerala | Thrissur | Hotel | 38 | 2026-02-08 | 2026-06-15 | 2026-06-22 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ006 | City Centre Mall | Central Kerala | Kochi | Shopping Mall | 55 | 2026-02-15 | 2026-08-30 |  |  | Material Delivered | In Progress | Pending | In Progress | 1 | 1
PRJ007 | Harmony Heights | South Kerala | Kollam | Residential | 27 | 2026-01-20 | 2026-05-20 | 2026-05-18 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ008 | River View Residency | North Kerala | Kozhikode | Residential | 21 | 2026-03-05 | 2026-06-30 | 2026-07-05 | 5 | Handover | Completed | Completed | Delayed |  | 1
PRJ009 | Tech Square Offices | Central Kerala | Kochi | Office | 48 | 2026-02-12 | 2026-07-15 | 2026-07-14 | -1 | Handover | Completed | Completed | Early |  | 1
PRJ010 | Sunrise Towers | North Kerala | Kannur | Commercial | 32 | 2026-04-01 | 2026-09-30 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1 |  | 58 | Completed
PRJ011 | Green Valley Apartments 011 | Central Kerala | Idukki | Hotel | 18 | 2026-01-01 | 2026-04-01 | 2026-03-27 | -5 | Testing & Commissioning | In Progress | Pending | Early |  | 1 |  | 247 | In Progress
PRJ012 | Royal Palm Apartments 012 | South Kerala | Alappuzha | Commercial | 24 | 2026-01-08 | 2026-05-08 | 2026-05-08 | 0 | Handover | Completed | Completed | On Time |  | 1 |  | 50 | Customer Type - Hospital
PRJ013 | Skyline Apartments 013 | North Kerala | Kannur | Residential | 42 | 2026-01-15 | 2026-06-14 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1 |  | 305
PRJ014 | Harmony Apartments 014 | Central Kerala | Thrissur | Apartment | 65 | 2026-01-22 | 2026-07-21 | 2026-07-19 | -2 | Material Delivered | In Progress | Pending | Early |  | 1 |  | 0
PRJ015 | Lakeside Apartments 015 | South Kerala | Pathanamthitta | Hospital | 38 | 2026-01-29 | 2026-08-27 | 2026-09-06 | 10 | Installation Started | In Progress | Pending | Delayed |  | 1 |  | 0
PRJ016 | Sunrise Apartments 016 | North Kerala | Kasaragod | Office | 55 | 2026-02-05 | 2026-05-06 | 2026-05-01 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ017 | Silver Oak Apartments 017 | Central Kerala | Idukki | Hotel | 27 | 2026-02-12 | 2026-06-12 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ018 | River View Apartments 018 | South Kerala | Kollam | Commercial | 21 | 2026-02-19 | 2026-07-19 | 2026-07-26 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ019 | Golden Gate Apartments 019 | North Kerala | Wayanad | Residential | 48 | 2026-02-26 | 2026-08-25 | 2026-08-23 | -2 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ020 | Emerald Apartments 020 | Central Kerala | Thrissur | Apartment | 32 | 2026-03-05 | 2026-10-01 | 2026-10-11 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ021 | Green Valley Heights 021 | South Kerala | Trivandrum | Hospital | 18 | 2026-03-12 | 2026-06-10 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ022 | Royal Palm Heights 022 | North Kerala | Kozhikode | Office | 24 | 2026-03-19 | 2026-07-17 | 2026-07-17 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ023 | Skyline Heights 023 | Central Kerala | Idukki | Hotel | 42 | 2026-03-26 | 2026-08-23 | 2026-08-30 | 7 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ024 | Harmony Heights 024 | South Kerala | Alappuzha | Commercial | 65 | 2026-04-02 | 2026-09-29 | 2026-09-27 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ025 | Lakeside Heights 025 | North Kerala | Kannur | Residential | 38 | 2026-04-09 | 2026-11-05 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ026 | Sunrise Heights 026 | Central Kerala | Thrissur | Apartment | 55 | 2026-04-16 | 2026-07-15 | 2026-07-10 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ027 | Silver Oak Heights 027 | South Kerala | Pathanamthitta | Hospital | 27 | 2026-04-23 | 2026-08-21 | 2026-08-21 | 0 | Installation Started | In Progress | Pending | On Time |  | 1
PRJ028 | River View Heights 028 | North Kerala | Kasaragod | Office | 21 | 2026-04-30 | 2026-09-27 | 2026-10-04 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ029 | Golden Gate Heights 029 | Central Kerala | Idukki | Hotel | 48 | 2026-05-07 | 2026-11-03 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ030 | Emerald Heights 030 | South Kerala | Kollam | Commercial | 32 | 2026-05-14 | 2026-12-10 | 2026-12-20 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ031 | Green Valley Towers 031 | North Kerala | Wayanad | Residential | 18 | 2026-05-21 | 2026-08-19 | 2026-08-14 | -5 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ032 | Royal Palm Towers 032 | Central Kerala | Thrissur | Apartment | 24 | 2026-05-28 | 2026-09-25 | 2026-09-25 | 0 | Material Delivered | In Progress | Pending | On Time |  | 1
PRJ033 | Skyline Towers 033 | South Kerala | Trivandrum | Hospital | 42 | 2026-06-04 | 2026-11-01 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ034 | Harmony Towers 034 | North Kerala | Kozhikode | Office | 65 | 2026-06-11 | 2026-12-08 | 2026-12-06 | -2 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ035 | Lakeside Towers 035 | Central Kerala | Idukki | Hotel | 38 | 2026-06-18 | 2027-01-14 | 2027-01-24 | 10 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ036 | Sunrise Towers 036 | South Kerala | Alappuzha | Commercial | 55 | 2026-06-25 | 2026-09-23 | 2026-09-18 | -5 | Handover | Completed | Completed | Early |  | 1
PRJ037 | Silver Oak Towers 037 | North Kerala | Kannur | Residential | 27 | 2026-01-03 | 2026-05-03 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ038 | River View Towers 038 | Central Kerala | Thrissur | Apartment | 21 | 2026-01-10 | 2026-06-09 | 2026-06-16 | 7 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ039 | Golden Gate Towers 039 | South Kerala | Pathanamthitta | Hospital | 48 | 2026-01-17 | 2026-07-16 | 2026-07-14 | -2 | Installation Started | In Progress | Pending | Early |  | 1
PRJ040 | Emerald Towers 040 | North Kerala | Kasaragod | Office | 32 | 2026-01-24 | 2026-08-22 | 2026-09-01 | 10 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ041 | Green Valley Enclave 041 | Central Kerala | Idukki | Hotel | 18 | 2026-01-31 | 2026-05-01 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ042 | Royal Palm Enclave 042 | South Kerala | Kollam | Commercial | 24 | 2026-02-07 | 2026-06-07 | 2026-06-07 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ043 | Skyline Enclave 043 | North Kerala | Wayanad | Residential | 42 | 2026-02-14 | 2026-07-14 | 2026-07-21 | 7 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ044 | Harmony Enclave 044 | Central Kerala | Thrissur | Apartment | 65 | 2026-02-21 | 2026-08-20 | 2026-08-18 | -2 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ045 | Lakeside Enclave 045 | South Kerala | Trivandrum | Hospital | 38 | 2026-02-28 | 2026-09-26 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ046 | Sunrise Enclave 046 | North Kerala | Kozhikode | Office | 55 | 2026-03-07 | 2026-06-05 | 2026-05-31 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ047 | Silver Oak Enclave 047 | Central Kerala | Idukki | Hotel | 27 | 2026-03-14 | 2026-07-12 | 2026-07-12 | 0 | Testing & Commissioning | In Progress | Pending | On Time |  | 1
PRJ048 | River View Enclave 048 | South Kerala | Alappuzha | Commercial | 21 | 2026-03-21 | 2026-08-18 | 2026-08-25 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ049 | Golden Gate Enclave 049 | North Kerala | Kannur | Residential | 48 | 2026-03-28 | 2026-09-24 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ050 | Emerald Enclave 050 | Central Kerala | Thrissur | Apartment | 32 | 2026-04-04 | 2026-10-31 | 2026-11-10 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ051 | Green Valley Business Centre 051 | South Kerala | Pathanamthitta | Hospital | 18 | 2026-04-11 | 2026-07-10 | 2026-07-05 | -5 | Installation Started | In Progress | Pending | Early |  | 1
PRJ052 | Royal Palm Business Centre 052 | North Kerala | Kasaragod | Office | 24 | 2026-04-18 | 2026-08-16 | 2026-08-16 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ053 | Skyline Business Centre 053 | Central Kerala | Idukki | Hotel | 42 | 2026-04-25 | 2026-09-22 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ054 | Harmony Business Centre 054 | South Kerala | Kollam | Commercial | 65 | 2026-05-02 | 2026-10-29 | 2026-10-27 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ055 | Lakeside Business Centre 055 | North Kerala | Wayanad | Residential | 38 | 2026-05-09 | 2026-12-05 | 2026-12-15 | 10 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ056 | Sunrise Business Centre 056 | Central Kerala | Thrissur | Apartment | 55 | 2026-05-16 | 2026-08-14 | 2026-08-09 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ057 | Silver Oak Business Centre 057 | South Kerala | Trivandrum | Hospital | 27 | 2026-05-23 | 2026-09-20 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ058 | River View Business Centre 058 | North Kerala | Kozhikode | Office | 21 | 2026-05-30 | 2026-10-27 | 2026-11-03 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ059 | Golden Gate Business Centre 059 | Central Kerala | Idukki | Hotel | 48 | 2026-06-06 | 2026-12-03 | 2026-12-01 | -2 | Testing & Commissioning | In Progress | Pending | Early |  | 1
PRJ060 | Emerald Business Centre 060 | South Kerala | Alappuzha | Commercial | 32 | 2026-06-13 | 2027-01-09 | 2027-01-19 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ061 | Green Valley Grand Hotel 061 | North Kerala | Kannur | Residential | 18 | 2026-06-20 | 2026-09-18 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ062 | Royal Palm Grand Hotel 062 | Central Kerala | Thrissur | Apartment | 24 | 2026-06-27 | 2026-10-25 | 2026-10-25 | 0 | Material Delivered | In Progress | Pending | On Time |  | 1
PRJ063 | Skyline Grand Hotel 063 | South Kerala | Pathanamthitta | Hospital | 42 | 2026-01-05 | 2026-06-04 | 2026-06-11 | 7 | Installation Started | In Progress | Pending | Delayed |  | 1
PRJ064 | Harmony Grand Hotel 064 | North Kerala | Kasaragod | Office | 65 | 2026-01-12 | 2026-07-11 | 2026-07-09 | -2 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ065 | Lakeside Grand Hotel 065 | Central Kerala | Idukki | Hotel | 38 | 2026-01-19 | 2026-08-17 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ066 | Sunrise Grand Hotel 066 | South Kerala | Kollam | Commercial | 55 | 2026-01-26 | 2026-04-26 | 2026-04-21 | -5 | Handover | Completed | Completed | Early |  | 1
PRJ067 | Silver Oak Grand Hotel 067 | North Kerala | Wayanad | Residential | 27 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 0 | Material Ordered | In Progress | Pending | On Time |  | 1
PRJ068 | River View Grand Hotel 068 | Central Kerala | Thrissur | Apartment | 21 | 2026-02-09 | 2026-07-09 | 2026-07-16 | 7 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ069 | Golden Gate Grand Hotel 069 | South Kerala | Trivandrum | Hospital | 48 | 2026-02-16 | 2026-08-15 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ070 | Emerald Grand Hotel 070 | North Kerala | Kozhikode | Office | 32 | 2026-02-23 | 2026-09-21 | 2026-10-01 | 10 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ071 | Green Valley Care Hospital 071 | Central Kerala | Idukki | Hotel | 18 | 2026-03-02 | 2026-05-31 | 2026-05-26 | -5 | Testing & Commissioning | In Progress | Pending | Early |  | 1
PRJ072 | Royal Palm Care Hospital 072 | South Kerala | Alappuzha | Commercial | 24 | 2026-03-09 | 2026-07-07 | 2026-07-07 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ073 | Skyline Care Hospital 073 | North Kerala | Kannur | Residential | 42 | 2026-03-16 | 2026-08-13 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ074 | Harmony Care Hospital 074 | Central Kerala | Thrissur | Apartment | 65 | 2026-03-23 | 2026-09-19 | 2026-09-17 | -2 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ075 | Lakeside Care Hospital 075 | South Kerala | Pathanamthitta | Hospital | 38 | 2026-03-30 | 2026-10-26 | 2026-11-05 | 10 | Installation Started | In Progress | Pending | Delayed |  | 1
PRJ076 | Sunrise Care Hospital 076 | North Kerala | Kasaragod | Office | 55 | 2026-04-06 | 2026-07-05 | 2026-06-30 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ077 | Silver Oak Care Hospital 077 | Central Kerala | Idukki | Hotel | 27 | 2026-04-13 | 2026-08-11 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ078 | River View Care Hospital 078 | South Kerala | Kollam | Commercial | 21 | 2026-04-20 | 2026-09-17 | 2026-09-24 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ079 | Golden Gate Care Hospital 079 | North Kerala | Wayanad | Residential | 48 | 2026-04-27 | 2026-10-24 | 2026-10-22 | -2 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ080 | Emerald Care Hospital 080 | Central Kerala | Thrissur | Apartment | 32 | 2026-05-04 | 2026-11-30 | 2026-12-10 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ081 | Green Valley Residency 081 | South Kerala | Trivandrum | Hospital | 18 | 2026-05-11 | 2026-08-09 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ082 | Royal Palm Residency 082 | North Kerala | Kozhikode | Office | 24 | 2026-05-18 | 2026-09-15 | 2026-09-15 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ083 | Skyline Residency 083 | Central Kerala | Idukki | Hotel | 42 | 2026-05-25 | 2026-10-22 | 2026-10-29 | 7 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ084 | Harmony Residency 084 | South Kerala | Alappuzha | Commercial | 65 | 2026-06-01 | 2026-11-28 | 2026-11-26 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ085 | Lakeside Residency 085 | North Kerala | Kannur | Residential | 38 | 2026-06-08 | 2027-01-04 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ086 | Sunrise Residency 086 | Central Kerala | Thrissur | Apartment | 55 | 2026-06-15 | 2026-09-13 | 2026-09-08 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ087 | Silver Oak Residency 087 | South Kerala | Pathanamthitta | Hospital | 27 | 2026-06-22 | 2026-10-20 | 2026-10-20 | 0 | Installation Started | In Progress | Pending | On Time |  | 1
PRJ088 | River View Residency 088 | North Kerala | Kasaragod | Office | 21 | 2026-06-29 | 2026-11-26 | 2026-12-03 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ089 | Golden Gate Residency 089 | Central Kerala | Idukki | Hotel | 48 | 2026-01-07 | 2026-07-06 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ090 | Emerald Residency 090 | South Kerala | Kollam | Commercial | 32 | 2026-01-14 | 2026-08-12 | 2026-08-22 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ091 | Green Valley Apartments 091 | North Kerala | Wayanad | Residential | 18 | 2026-01-21 | 2026-04-21 | 2026-04-16 | -5 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ092 | Royal Palm Apartments 092 | Central Kerala | Thrissur | Apartment | 24 | 2026-01-28 | 2026-05-28 | 2026-05-28 | 0 | Material Delivered | In Progress | Pending | On Time |  | 1
PRJ093 | Skyline Apartments 093 | South Kerala | Trivandrum | Hospital | 42 | 2026-02-04 | 2026-07-04 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ094 | Harmony Apartments 094 | North Kerala | Kozhikode | Office | 65 | 2026-02-11 | 2026-08-10 | 2026-08-08 | -2 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ095 | Lakeside Apartments 095 | Central Kerala | Idukki | Hotel | 38 | 2026-02-18 | 2026-09-16 | 2026-09-26 | 10 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ096 | Sunrise Apartments 096 | South Kerala | Alappuzha | Commercial | 55 | 2026-02-25 | 2026-05-26 | 2026-05-21 | -5 | Handover | Completed | Completed | Early |  | 1
PRJ097 | Silver Oak Apartments 097 | North Kerala | Kannur | Residential | 27 | 2026-03-04 | 2026-07-02 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ098 | River View Apartments 098 | Central Kerala | Thrissur | Apartment | 21 | 2026-03-11 | 2026-08-08 | 2026-08-15 | 7 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ099 | Golden Gate Apartments 099 | South Kerala | Pathanamthitta | Hospital | 48 | 2026-03-18 | 2026-09-14 | 2026-09-12 | -2 | Installation Started | In Progress | Pending | Early |  | 1
PRJ100 | Emerald Apartments 100 | North Kerala | Kasaragod | Office | 32 | 2026-03-25 | 2026-10-21 | 2026-10-31 | 10 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ101 | Green Valley Heights 101 | Central Kerala | Idukki | Hotel | 18 | 2026-04-01 | 2026-06-30 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ102 | Royal Palm Heights 102 | South Kerala | Kollam | Commercial | 24 | 2026-04-08 | 2026-08-06 | 2026-08-06 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ103 | Skyline Heights 103 | North Kerala | Wayanad | Residential | 42 | 2026-04-15 | 2026-09-12 | 2026-09-19 | 7 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ104 | Harmony Heights 104 | Central Kerala | Thrissur | Apartment | 65 | 2026-04-22 | 2026-10-19 | 2026-10-17 | -2 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ105 | Lakeside Heights 105 | South Kerala | Trivandrum | Hospital | 38 | 2026-04-29 | 2026-11-25 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ106 | Sunrise Heights 106 | North Kerala | Kozhikode | Office | 55 | 2026-05-06 | 2026-08-04 | 2026-07-30 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ107 | Silver Oak Heights 107 | Central Kerala | Idukki | Hotel | 27 | 2026-05-13 | 2026-09-10 | 2026-09-10 | 0 | Testing & Commissioning | In Progress | Pending | On Time |  | 1
PRJ108 | River View Heights 108 | South Kerala | Alappuzha | Commercial | 21 | 2026-05-20 | 2026-10-17 | 2026-10-24 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ109 | Golden Gate Heights 109 | North Kerala | Kannur | Residential | 48 | 2026-05-27 | 2026-11-23 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ110 | Emerald Heights 110 | Central Kerala | Thrissur | Apartment | 32 | 2026-06-03 | 2026-12-30 | 2027-01-09 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ111 | Green Valley Towers 111 | South Kerala | Pathanamthitta | Hospital | 18 | 2026-06-10 | 2026-09-08 | 2026-09-03 | -5 | Installation Started | In Progress | Pending | Early |  | 1
PRJ112 | Royal Palm Towers 112 | North Kerala | Kasaragod | Office | 24 | 2026-06-17 | 2026-10-15 | 2026-10-15 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ113 | Skyline Towers 113 | Central Kerala | Idukki | Hotel | 42 | 2026-06-24 | 2026-11-21 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ114 | Harmony Towers 114 | South Kerala | Kollam | Commercial | 65 | 2026-01-02 | 2026-07-01 | 2026-06-29 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ115 | Lakeside Towers 115 | North Kerala | Wayanad | Residential | 38 | 2026-01-09 | 2026-08-07 | 2026-08-17 | 10 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ116 | Sunrise Towers 116 | Central Kerala | Thrissur | Apartment | 55 | 2026-01-16 | 2026-04-16 | 2026-04-11 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ117 | Silver Oak Towers 117 | South Kerala | Trivandrum | Hospital | 27 | 2026-01-23 | 2026-05-23 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ118 | River View Towers 118 | North Kerala | Kozhikode | Office | 21 | 2026-01-30 | 2026-06-29 | 2026-07-06 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ119 | Golden Gate Towers 119 | Central Kerala | Idukki | Hotel | 48 | 2026-02-06 | 2026-08-05 | 2026-08-03 | -2 | Testing & Commissioning | In Progress | Pending | Early |  | 1
PRJ120 | Emerald Towers 120 | South Kerala | Alappuzha | Commercial | 32 | 2026-02-13 | 2026-09-11 | 2026-09-21 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ121 | Green Valley Enclave 121 | North Kerala | Kannur | Residential | 18 | 2026-02-20 | 2026-05-21 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ122 | Royal Palm Enclave 122 | Central Kerala | Thrissur | Apartment | 24 | 2026-02-27 | 2026-06-27 | 2026-06-27 | 0 | Material Delivered | In Progress | Pending | On Time |  | 1
PRJ123 | Skyline Enclave 123 | South Kerala | Pathanamthitta | Hospital | 42 | 2026-03-06 | 2026-08-03 | 2026-08-10 | 7 | Installation Started | In Progress | Pending | Delayed |  | 1
PRJ124 | Harmony Enclave 124 | North Kerala | Kasaragod | Office | 65 | 2026-03-13 | 2026-09-09 | 2026-09-07 | -2 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ125 | Lakeside Enclave 125 | Central Kerala | Idukki | Hotel | 38 | 2026-03-20 | 2026-10-16 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ126 | Sunrise Enclave 126 | South Kerala | Kollam | Commercial | 55 | 2026-03-27 | 2026-06-25 | 2026-06-20 | -5 | Handover | Completed | Completed | Early |  | 1
PRJ127 | Silver Oak Enclave 127 | North Kerala | Wayanad | Residential | 27 | 2026-04-03 | 2026-08-01 | 2026-08-01 | 0 | Material Ordered | In Progress | Pending | On Time |  | 1
PRJ128 | River View Enclave 128 | Central Kerala | Thrissur | Apartment | 21 | 2026-04-10 | 2026-09-07 | 2026-09-14 | 7 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ129 | Golden Gate Enclave 129 | South Kerala | Trivandrum | Hospital | 48 | 2026-04-17 | 2026-10-14 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ130 | Emerald Enclave 130 | North Kerala | Kozhikode | Office | 32 | 2026-04-24 | 2026-11-20 | 2026-11-30 | 10 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ131 | Green Valley Business Centre 131 | Central Kerala | Idukki | Hotel | 18 | 2026-05-01 | 2026-07-30 | 2026-07-25 | -5 | Testing & Commissioning | In Progress | Pending | Early |  | 1
PRJ132 | Royal Palm Business Centre 132 | South Kerala | Alappuzha | Commercial | 24 | 2026-05-08 | 2026-09-05 | 2026-09-05 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ133 | Skyline Business Centre 133 | North Kerala | Kannur | Residential | 42 | 2026-05-15 | 2026-10-12 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ134 | Harmony Business Centre 134 | Central Kerala | Thrissur | Apartment | 65 | 2026-05-22 | 2026-11-18 | 2026-11-16 | -2 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ135 | Lakeside Business Centre 135 | South Kerala | Pathanamthitta | Hospital | 38 | 2026-05-29 | 2026-12-25 | 2027-01-04 | 10 | Installation Started | In Progress | Pending | Delayed |  | 1
PRJ136 | Sunrise Business Centre 136 | North Kerala | Kasaragod | Office | 55 | 2026-06-05 | 2026-09-03 | 2026-08-29 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ137 | Silver Oak Business Centre 137 | Central Kerala | Idukki | Hotel | 27 | 2026-06-12 | 2026-10-10 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ138 | River View Business Centre 138 | South Kerala | Kollam | Commercial | 21 | 2026-06-19 | 2026-11-16 | 2026-11-23 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ139 | Golden Gate Business Centre 139 | North Kerala | Wayanad | Residential | 48 | 2026-06-26 | 2026-12-23 | 2026-12-21 | -2 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ140 | Emerald Business Centre 140 | Central Kerala | Thrissur | Apartment | 32 | 2026-01-04 | 2026-08-02 | 2026-08-12 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ141 | Green Valley Grand Hotel 141 | South Kerala | Trivandrum | Hospital | 18 | 2026-01-11 | 2026-04-11 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ142 | Royal Palm Grand Hotel 142 | North Kerala | Kozhikode | Office | 24 | 2026-01-18 | 2026-05-18 | 2026-05-18 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ143 | Skyline Grand Hotel 143 | Central Kerala | Idukki | Hotel | 42 | 2026-01-25 | 2026-06-24 | 2026-07-01 | 7 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ144 | Harmony Grand Hotel 144 | South Kerala | Alappuzha | Commercial | 65 | 2026-02-01 | 2026-07-31 | 2026-07-29 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ145 | Lakeside Grand Hotel 145 | North Kerala | Kannur | Residential | 38 | 2026-02-08 | 2026-09-06 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ146 | Sunrise Grand Hotel 146 | Central Kerala | Thrissur | Apartment | 55 | 2026-02-15 | 2026-05-16 | 2026-05-11 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ147 | Silver Oak Grand Hotel 147 | South Kerala | Pathanamthitta | Hospital | 27 | 2026-02-22 | 2026-06-22 | 2026-06-22 | 0 | Installation Started | In Progress | Pending | On Time |  | 1
PRJ148 | River View Grand Hotel 148 | North Kerala | Kasaragod | Office | 21 | 2026-03-01 | 2026-07-29 | 2026-08-05 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ149 | Golden Gate Grand Hotel 149 | Central Kerala | Idukki | Hotel | 48 | 2026-03-08 | 2026-09-04 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ150 | Emerald Grand Hotel 150 | South Kerala | Kollam | Commercial | 32 | 2026-03-15 | 2026-10-11 | 2026-10-21 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ151 | Green Valley Care Hospital 151 | North Kerala | Wayanad | Residential | 18 | 2026-03-22 | 2026-06-20 | 2026-06-15 | -5 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ152 | Royal Palm Care Hospital 152 | Central Kerala | Thrissur | Apartment | 24 | 2026-03-29 | 2026-07-27 | 2026-07-27 | 0 | Material Delivered | In Progress | Pending | On Time |  | 1
PRJ153 | Skyline Care Hospital 153 | South Kerala | Trivandrum | Hospital | 42 | 2026-04-05 | 2026-09-02 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ154 | Harmony Care Hospital 154 | North Kerala | Kozhikode | Office | 65 | 2026-04-12 | 2026-10-09 | 2026-10-07 | -2 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ155 | Lakeside Care Hospital 155 | Central Kerala | Idukki | Hotel | 38 | 2026-04-19 | 2026-11-15 | 2026-11-25 | 10 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ156 | Sunrise Care Hospital 156 | South Kerala | Alappuzha | Commercial | 55 | 2026-04-26 | 2026-07-25 | 2026-07-20 | -5 | Handover | Completed | Completed | Early |  | 1
PRJ157 | Silver Oak Care Hospital 157 | North Kerala | Kannur | Residential | 27 | 2026-05-03 | 2026-08-31 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ158 | River View Care Hospital 158 | Central Kerala | Thrissur | Apartment | 21 | 2026-05-10 | 2026-10-07 | 2026-10-14 | 7 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ159 | Golden Gate Care Hospital 159 | South Kerala | Pathanamthitta | Hospital | 48 | 2026-05-17 | 2026-11-13 | 2026-11-11 | -2 | Installation Started | In Progress | Pending | Early |  | 1
PRJ160 | Emerald Care Hospital 160 | North Kerala | Kasaragod | Office | 32 | 2026-05-24 | 2026-12-20 | 2026-12-30 | 10 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ161 | Green Valley Residency 161 | Central Kerala | Idukki | Hotel | 18 | 2026-05-31 | 2026-08-29 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ162 | Royal Palm Residency 162 | South Kerala | Kollam | Commercial | 24 | 2026-06-07 | 2026-10-05 | 2026-10-05 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ163 | Skyline Residency 163 | North Kerala | Wayanad | Residential | 42 | 2026-06-14 | 2026-11-11 | 2026-11-18 | 7 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ164 | Harmony Residency 164 | Central Kerala | Thrissur | Apartment | 65 | 2026-06-21 | 2026-12-18 | 2026-12-16 | -2 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ165 | Lakeside Residency 165 | South Kerala | Trivandrum | Hospital | 38 | 2026-06-28 | 2027-01-24 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ166 | Sunrise Residency 166 | North Kerala | Kozhikode | Office | 55 | 2026-01-06 | 2026-04-06 | 2026-04-01 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ167 | Silver Oak Residency 167 | Central Kerala | Idukki | Hotel | 27 | 2026-01-13 | 2026-05-13 | 2026-05-13 | 0 | Testing & Commissioning | In Progress | Pending | On Time |  | 1
PRJ168 | River View Residency 168 | South Kerala | Alappuzha | Commercial | 21 | 2026-01-20 | 2026-06-19 | 2026-06-26 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ169 | Golden Gate Residency 169 | North Kerala | Kannur | Residential | 48 | 2026-01-27 | 2026-07-26 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ170 | Emerald Residency 170 | Central Kerala | Thrissur | Apartment | 32 | 2026-02-03 | 2026-09-01 | 2026-09-11 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ171 | Green Valley Apartments 171 | South Kerala | Pathanamthitta | Hospital | 18 | 2026-02-10 | 2026-05-11 | 2026-05-06 | -5 | Installation Started | In Progress | Pending | Early |  | 1
PRJ172 | Royal Palm Apartments 172 | North Kerala | Kasaragod | Office | 24 | 2026-02-17 | 2026-06-17 | 2026-06-17 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ173 | Skyline Apartments 173 | Central Kerala | Idukki | Hotel | 42 | 2026-02-24 | 2026-07-24 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ174 | Harmony Apartments 174 | South Kerala | Kollam | Commercial | 65 | 2026-03-03 | 2026-08-30 | 2026-08-28 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ175 | Lakeside Apartments 175 | North Kerala | Wayanad | Residential | 38 | 2026-03-10 | 2026-10-06 | 2026-10-16 | 10 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ176 | Sunrise Apartments 176 | Central Kerala | Thrissur | Apartment | 55 | 2026-03-17 | 2026-06-15 | 2026-06-10 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ177 | Silver Oak Apartments 177 | South Kerala | Trivandrum | Hospital | 27 | 2026-03-24 | 2026-07-22 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ178 | River View Apartments 178 | North Kerala | Kozhikode | Office | 21 | 2026-03-31 | 2026-08-28 | 2026-09-04 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ179 | Golden Gate Apartments 179 | Central Kerala | Idukki | Hotel | 48 | 2026-04-07 | 2026-10-04 | 2026-10-02 | -2 | Testing & Commissioning | In Progress | Pending | Early |  | 1
PRJ180 | Emerald Apartments 180 | South Kerala | Alappuzha | Commercial | 32 | 2026-04-14 | 2026-11-10 | 2026-11-20 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ181 | Green Valley Heights 181 | North Kerala | Kannur | Residential | 18 | 2026-04-21 | 2026-07-20 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ182 | Royal Palm Heights 182 | Central Kerala | Thrissur | Apartment | 24 | 2026-04-28 | 2026-08-26 | 2026-08-26 | 0 | Material Delivered | In Progress | Pending | On Time |  | 1
PRJ183 | Skyline Heights 183 | South Kerala | Pathanamthitta | Hospital | 42 | 2026-05-05 | 2026-10-02 | 2026-10-09 | 7 | Installation Started | In Progress | Pending | Delayed |  | 1
PRJ184 | Harmony Heights 184 | North Kerala | Kasaragod | Office | 65 | 2026-05-12 | 2026-11-08 | 2026-11-06 | -2 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ185 | Lakeside Heights 185 | Central Kerala | Idukki | Hotel | 38 | 2026-05-19 | 2026-12-15 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ186 | Sunrise Heights 186 | South Kerala | Kollam | Commercial | 55 | 2026-05-26 | 2026-08-24 | 2026-08-19 | -5 | Handover | Completed | Completed | Early |  | 1
PRJ187 | Silver Oak Heights 187 | North Kerala | Wayanad | Residential | 27 | 2026-06-02 | 2026-09-30 | 2026-09-30 | 0 | Material Ordered | In Progress | Pending | On Time |  | 1
PRJ188 | River View Heights 188 | Central Kerala | Thrissur | Apartment | 21 | 2026-06-09 | 2026-11-06 | 2026-11-13 | 7 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ189 | Golden Gate Heights 189 | South Kerala | Trivandrum | Hospital | 48 | 2026-06-16 | 2026-12-13 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ190 | Emerald Heights 190 | North Kerala | Kozhikode | Office | 32 | 2026-06-23 | 2027-01-19 | 2027-01-29 | 10 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ191 | Green Valley Towers 191 | Central Kerala | Idukki | Hotel | 18 | 2026-01-01 | 2026-04-01 | 2026-03-27 | -5 | Testing & Commissioning | In Progress | Pending | Early |  | 1
PRJ192 | Royal Palm Towers 192 | South Kerala | Alappuzha | Commercial | 24 | 2026-01-08 | 2026-05-08 | 2026-05-08 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ193 | Skyline Towers 193 | North Kerala | Kannur | Residential | 42 | 2026-01-15 | 2026-06-14 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ194 | Harmony Towers 194 | Central Kerala | Thrissur | Apartment | 65 | 2026-01-22 | 2026-07-21 | 2026-07-19 | -2 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ195 | Lakeside Towers 195 | South Kerala | Pathanamthitta | Hospital | 38 | 2026-01-29 | 2026-08-27 | 2026-09-06 | 10 | Installation Started | In Progress | Pending | Delayed |  | 1
PRJ196 | Sunrise Towers 196 | North Kerala | Kasaragod | Office | 55 | 2026-02-05 | 2026-05-06 | 2026-05-01 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ197 | Silver Oak Towers 197 | Central Kerala | Idukki | Hotel | 27 | 2026-02-12 | 2026-06-12 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ198 | River View Towers 198 | South Kerala | Kollam | Commercial | 21 | 2026-02-19 | 2026-07-19 | 2026-07-26 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ199 | Golden Gate Towers 199 | North Kerala | Wayanad | Residential | 48 | 2026-02-26 | 2026-08-25 | 2026-08-23 | -2 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ200 | Emerald Towers 200 | Central Kerala | Thrissur | Apartment | 32 | 2026-03-05 | 2026-10-01 | 2026-10-11 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ201 | Green Valley Enclave 201 | South Kerala | Trivandrum | Hospital | 18 | 2026-03-12 | 2026-06-10 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ202 | Royal Palm Enclave 202 | North Kerala | Kozhikode | Office | 24 | 2026-03-19 | 2026-07-17 | 2026-07-17 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ203 | Skyline Enclave 203 | Central Kerala | Idukki | Hotel | 42 | 2026-03-26 | 2026-08-23 | 2026-08-30 | 7 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ204 | Harmony Enclave 204 | South Kerala | Alappuzha | Commercial | 65 | 2026-04-02 | 2026-09-29 | 2026-09-27 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ205 | Lakeside Enclave 205 | North Kerala | Kannur | Residential | 38 | 2026-04-09 | 2026-11-05 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ206 | Sunrise Enclave 206 | Central Kerala | Thrissur | Apartment | 55 | 2026-04-16 | 2026-07-15 | 2026-07-10 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ207 | Silver Oak Enclave 207 | South Kerala | Pathanamthitta | Hospital | 27 | 2026-04-23 | 2026-08-21 | 2026-08-21 | 0 | Installation Started | In Progress | Pending | On Time |  | 1
PRJ208 | River View Enclave 208 | North Kerala | Kasaragod | Office | 21 | 2026-04-30 | 2026-09-27 | 2026-10-04 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ209 | Golden Gate Enclave 209 | Central Kerala | Idukki | Hotel | 48 | 2026-05-07 | 2026-11-03 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ210 | Emerald Enclave 210 | South Kerala | Kollam | Commercial | 32 | 2026-05-14 | 2026-12-10 | 2026-12-20 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ211 | Green Valley Business Centre 211 | North Kerala | Wayanad | Residential | 18 | 2026-05-21 | 2026-08-19 | 2026-08-14 | -5 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ212 | Royal Palm Business Centre 212 | Central Kerala | Thrissur | Apartment | 24 | 2026-05-28 | 2026-09-25 | 2026-09-25 | 0 | Material Delivered | In Progress | Pending | On Time |  | 1
PRJ213 | Skyline Business Centre 213 | South Kerala | Trivandrum | Hospital | 42 | 2026-06-04 | 2026-11-01 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ214 | Harmony Business Centre 214 | North Kerala | Kozhikode | Office | 65 | 2026-06-11 | 2026-12-08 | 2026-12-06 | -2 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ215 | Lakeside Business Centre 215 | Central Kerala | Idukki | Hotel | 38 | 2026-06-18 | 2027-01-14 | 2027-01-24 | 10 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ216 | Sunrise Business Centre 216 | South Kerala | Alappuzha | Commercial | 55 | 2026-06-25 | 2026-09-23 | 2026-09-18 | -5 | Handover | Completed | Completed | Early |  | 1
PRJ217 | Silver Oak Business Centre 217 | North Kerala | Kannur | Residential | 27 | 2026-01-03 | 2026-05-03 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ218 | River View Business Centre 218 | Central Kerala | Thrissur | Apartment | 21 | 2026-01-10 | 2026-06-09 | 2026-06-16 | 7 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ219 | Golden Gate Business Centre 219 | South Kerala | Pathanamthitta | Hospital | 48 | 2026-01-17 | 2026-07-16 | 2026-07-14 | -2 | Installation Started | In Progress | Pending | Early |  | 1
PRJ220 | Emerald Business Centre 220 | North Kerala | Kasaragod | Office | 32 | 2026-01-24 | 2026-08-22 | 2026-09-01 | 10 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ221 | Green Valley Grand Hotel 221 | Central Kerala | Idukki | Hotel | 18 | 2026-01-31 | 2026-05-01 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ222 | Royal Palm Grand Hotel 222 | South Kerala | Kollam | Commercial | 24 | 2026-02-07 | 2026-06-07 | 2026-06-07 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ223 | Skyline Grand Hotel 223 | North Kerala | Wayanad | Residential | 42 | 2026-02-14 | 2026-07-14 | 2026-07-21 | 7 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ224 | Harmony Grand Hotel 224 | Central Kerala | Thrissur | Apartment | 65 | 2026-02-21 | 2026-08-20 | 2026-08-18 | -2 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ225 | Lakeside Grand Hotel 225 | South Kerala | Trivandrum | Hospital | 38 | 2026-02-28 | 2026-09-26 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ226 | Sunrise Grand Hotel 226 | North Kerala | Kozhikode | Office | 55 | 2026-03-07 | 2026-06-05 | 2026-05-31 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ227 | Silver Oak Grand Hotel 227 | Central Kerala | Idukki | Hotel | 27 | 2026-03-14 | 2026-07-12 | 2026-07-12 | 0 | Testing & Commissioning | In Progress | Pending | On Time |  | 1
PRJ228 | River View Grand Hotel 228 | South Kerala | Alappuzha | Commercial | 21 | 2026-03-21 | 2026-08-18 | 2026-08-25 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ229 | Golden Gate Grand Hotel 229 | North Kerala | Kannur | Residential | 48 | 2026-03-28 | 2026-09-24 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ230 | Emerald Grand Hotel 230 | Central Kerala | Thrissur | Apartment | 32 | 2026-04-04 | 2026-10-31 | 2026-11-10 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ231 | Green Valley Care Hospital 231 | South Kerala | Pathanamthitta | Hospital | 18 | 2026-04-11 | 2026-07-10 | 2026-07-05 | -5 | Installation Started | In Progress | Pending | Early |  | 1
PRJ232 | Royal Palm Care Hospital 232 | North Kerala | Kasaragod | Office | 24 | 2026-04-18 | 2026-08-16 | 2026-08-16 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ233 | Skyline Care Hospital 233 | Central Kerala | Idukki | Hotel | 42 | 2026-04-25 | 2026-09-22 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ234 | Harmony Care Hospital 234 | South Kerala | Kollam | Commercial | 65 | 2026-05-02 | 2026-10-29 | 2026-10-27 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ235 | Lakeside Care Hospital 235 | North Kerala | Wayanad | Residential | 38 | 2026-05-09 | 2026-12-05 | 2026-12-15 | 10 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ236 | Sunrise Care Hospital 236 | Central Kerala | Thrissur | Apartment | 55 | 2026-05-16 | 2026-08-14 | 2026-08-09 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ237 | Silver Oak Care Hospital 237 | South Kerala | Trivandrum | Hospital | 27 | 2026-05-23 | 2026-09-20 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ238 | River View Care Hospital 238 | North Kerala | Kozhikode | Office | 21 | 2026-05-30 | 2026-10-27 | 2026-11-03 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ239 | Golden Gate Care Hospital 239 | Central Kerala | Idukki | Hotel | 48 | 2026-06-06 | 2026-12-03 | 2026-12-01 | -2 | Testing & Commissioning | In Progress | Pending | Early |  | 1
PRJ240 | Emerald Care Hospital 240 | South Kerala | Alappuzha | Commercial | 32 | 2026-06-13 | 2027-01-09 | 2027-01-19 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ241 | Green Valley Residency 241 | North Kerala | Kannur | Residential | 18 | 2026-06-20 | 2026-09-18 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ242 | Royal Palm Residency 242 | Central Kerala | Thrissur | Apartment | 24 | 2026-06-27 | 2026-10-25 | 2026-10-25 | 0 | Material Delivered | In Progress | Pending | On Time |  | 1
PRJ243 | Skyline Residency 243 | South Kerala | Pathanamthitta | Hospital | 42 | 2026-01-05 | 2026-06-04 | 2026-06-11 | 7 | Installation Started | In Progress | Pending | Delayed |  | 1
PRJ244 | Harmony Residency 244 | North Kerala | Kasaragod | Office | 65 | 2026-01-12 | 2026-07-11 | 2026-07-09 | -2 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ245 | Lakeside Residency 245 | Central Kerala | Idukki | Hotel | 38 | 2026-01-19 | 2026-08-17 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ246 | Sunrise Residency 246 | South Kerala | Kollam | Commercial | 55 | 2026-01-26 | 2026-04-26 | 2026-04-21 | -5 | Handover | Completed | Completed | Early |  | 1
PRJ247 | Silver Oak Residency 247 | North Kerala | Wayanad | Residential | 27 | 2026-02-02 | 2026-06-02 | 2026-06-02 | 0 | Material Ordered | In Progress | Pending | On Time |  | 1
PRJ248 | River View Residency 248 | Central Kerala | Thrissur | Apartment | 21 | 2026-02-09 | 2026-07-09 | 2026-07-16 | 7 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ249 | Golden Gate Residency 249 | South Kerala | Trivandrum | Hospital | 48 | 2026-02-16 | 2026-08-15 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ250 | Emerald Residency 250 | North Kerala | Kozhikode | Office | 32 | 2026-02-23 | 2026-09-21 | 2026-10-01 | 10 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ251 | Green Valley Apartments 251 | Central Kerala | Idukki | Hotel | 18 | 2026-03-02 | 2026-05-31 | 2026-05-26 | -5 | Testing & Commissioning | In Progress | Pending | Early |  | 1
PRJ252 | Royal Palm Apartments 252 | South Kerala | Alappuzha | Commercial | 24 | 2026-03-09 | 2026-07-07 | 2026-07-07 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ253 | Skyline Apartments 253 | North Kerala | Kannur | Residential | 42 | 2026-03-16 | 2026-08-13 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ254 | Harmony Apartments 254 | Central Kerala | Thrissur | Apartment | 65 | 2026-03-23 | 2026-09-19 | 2026-09-17 | -2 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ255 | Lakeside Apartments 255 | South Kerala | Pathanamthitta | Hospital | 38 | 2026-03-30 | 2026-10-26 | 2026-11-05 | 10 | Installation Started | In Progress | Pending | Delayed |  | 1
PRJ256 | Sunrise Apartments 256 | North Kerala | Kasaragod | Office | 55 | 2026-04-06 | 2026-07-05 | 2026-06-30 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ257 | Silver Oak Apartments 257 | Central Kerala | Idukki | Hotel | 27 | 2026-04-13 | 2026-08-11 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ258 | River View Apartments 258 | South Kerala | Kollam | Commercial | 21 | 2026-04-20 | 2026-09-17 | 2026-09-24 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ259 | Golden Gate Apartments 259 | North Kerala | Wayanad | Residential | 48 | 2026-04-27 | 2026-10-24 | 2026-10-22 | -2 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ260 | Emerald Apartments 260 | Central Kerala | Thrissur | Apartment | 32 | 2026-05-04 | 2026-11-30 | 2026-12-10 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ261 | Green Valley Heights 261 | South Kerala | Trivandrum | Hospital | 18 | 2026-05-11 | 2026-08-09 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ262 | Royal Palm Heights 262 | North Kerala | Kozhikode | Office | 24 | 2026-05-18 | 2026-09-15 | 2026-09-15 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ263 | Skyline Heights 263 | Central Kerala | Idukki | Hotel | 42 | 2026-05-25 | 2026-10-22 | 2026-10-29 | 7 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ264 | Harmony Heights 264 | South Kerala | Alappuzha | Commercial | 65 | 2026-06-01 | 2026-11-28 | 2026-11-26 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ265 | Lakeside Heights 265 | North Kerala | Kannur | Residential | 38 | 2026-06-08 | 2027-01-04 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ266 | Sunrise Heights 266 | Central Kerala | Thrissur | Apartment | 55 | 2026-06-15 | 2026-09-13 | 2026-09-08 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ267 | Silver Oak Heights 267 | South Kerala | Pathanamthitta | Hospital | 27 | 2026-06-22 | 2026-10-20 | 2026-10-20 | 0 | Installation Started | In Progress | Pending | On Time |  | 1
PRJ268 | River View Heights 268 | North Kerala | Kasaragod | Office | 21 | 2026-06-29 | 2026-11-26 | 2026-12-03 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ269 | Golden Gate Heights 269 | Central Kerala | Idukki | Hotel | 48 | 2026-01-07 | 2026-07-06 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ270 | Emerald Heights 270 | South Kerala | Kollam | Commercial | 32 | 2026-01-14 | 2026-08-12 | 2026-08-22 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ271 | Green Valley Towers 271 | North Kerala | Wayanad | Residential | 18 | 2026-01-21 | 2026-04-21 | 2026-04-16 | -5 | Material Ordered | In Progress | Pending | Early |  | 1
PRJ272 | Royal Palm Towers 272 | Central Kerala | Thrissur | Apartment | 24 | 2026-01-28 | 2026-05-28 | 2026-05-28 | 0 | Material Delivered | In Progress | Pending | On Time |  | 1
PRJ273 | Skyline Towers 273 | South Kerala | Trivandrum | Hospital | 42 | 2026-02-04 | 2026-07-04 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ274 | Harmony Towers 274 | North Kerala | Kozhikode | Office | 65 | 2026-02-11 | 2026-08-10 | 2026-08-08 | -2 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ275 | Lakeside Towers 275 | Central Kerala | Idukki | Hotel | 38 | 2026-02-18 | 2026-09-16 | 2026-09-26 | 10 | Testing & Commissioning | In Progress | Pending | Delayed |  | 1
PRJ276 | Sunrise Towers 276 | South Kerala | Alappuzha | Commercial | 55 | 2026-02-25 | 2026-05-26 | 2026-05-21 | -5 | Handover | Completed | Completed | Early |  | 1
PRJ277 | Silver Oak Towers 277 | North Kerala | Kannur | Residential | 27 | 2026-03-04 | 2026-07-02 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ278 | River View Towers 278 | Central Kerala | Thrissur | Apartment | 21 | 2026-03-11 | 2026-08-08 | 2026-08-15 | 7 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ279 | Golden Gate Towers 279 | South Kerala | Pathanamthitta | Hospital | 48 | 2026-03-18 | 2026-09-14 | 2026-09-12 | -2 | Installation Started | In Progress | Pending | Early |  | 1
PRJ280 | Emerald Towers 280 | North Kerala | Kasaragod | Office | 32 | 2026-03-25 | 2026-10-21 | 2026-10-31 | 10 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ281 | Green Valley Enclave 281 | Central Kerala | Idukki | Hotel | 18 | 2026-04-01 | 2026-06-30 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ282 | Royal Palm Enclave 282 | South Kerala | Kollam | Commercial | 24 | 2026-04-08 | 2026-08-06 | 2026-08-06 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ283 | Skyline Enclave 283 | North Kerala | Wayanad | Residential | 42 | 2026-04-15 | 2026-09-12 | 2026-09-19 | 7 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ284 | Harmony Enclave 284 | Central Kerala | Thrissur | Apartment | 65 | 2026-04-22 | 2026-10-19 | 2026-10-17 | -2 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ285 | Lakeside Enclave 285 | South Kerala | Trivandrum | Hospital | 38 | 2026-04-29 | 2026-11-25 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ286 | Sunrise Enclave 286 | North Kerala | Kozhikode | Office | 55 | 2026-05-06 | 2026-08-04 | 2026-07-30 | -5 | Mechanical Completion | In Progress | Pending | Early |  | 1
PRJ287 | Silver Oak Enclave 287 | Central Kerala | Idukki | Hotel | 27 | 2026-05-13 | 2026-09-10 | 2026-09-10 | 0 | Testing & Commissioning | In Progress | Pending | On Time |  | 1
PRJ288 | River View Enclave 288 | South Kerala | Alappuzha | Commercial | 21 | 2026-05-20 | 2026-10-17 | 2026-10-24 | 7 | Handover | Completed | Completed | Delayed |  | 1
PRJ289 | Golden Gate Enclave 289 | North Kerala | Kannur | Residential | 48 | 2026-05-27 | 2026-11-23 |  |  | Material Ordered | In Progress | Pending | In Progress |  | 1
PRJ290 | Emerald Enclave 290 | Central Kerala | Thrissur | Apartment | 32 | 2026-06-03 | 2026-12-30 | 2027-01-09 | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ291 | Green Valley Business Centre 291 | South Kerala | Pathanamthitta | Hospital | 18 | 2026-06-10 | 2026-09-08 | 2026-09-03 | -5 | Installation Started | In Progress | Pending | Early |  | 1
PRJ292 | Royal Palm Business Centre 292 | North Kerala | Kasaragod | Office | 24 | 2026-06-17 | 2026-10-15 | 2026-10-15 | 0 | Mechanical Completion | In Progress | Pending | On Time |  | 1
PRJ293 | Skyline Business Centre 293 | Central Kerala | Idukki | Hotel | 42 | 2026-06-24 | 2026-11-21 |  |  | Testing & Commissioning | In Progress | Pending | In Progress |  | 1
PRJ294 | Harmony Business Centre 294 | South Kerala | Kollam | Commercial | 65 | 2026-01-02 | 2026-07-01 | 2026-06-29 | -2 | Handover | Completed | Completed | Early |  | 1
PRJ295 | Lakeside Business Centre 295 | North Kerala | Wayanad | Residential | 38 | 2026-01-09 | 2026-08-07 | 2026-08-17 | 10 | Material Ordered | In Progress | Pending | Delayed |  | 1
PRJ296 | Sunrise Business Centre 296 | Central Kerala | Thrissur | Apartment | 55 | 2026-01-16 | 2026-04-16 | 2026-04-11 | -5 | Material Delivered | In Progress | Pending | Early |  | 1
PRJ297 | Silver Oak Business Centre 297 | South Kerala | Trivandrum | Hospital | 27 | 2026-01-23 | 2026-05-23 |  |  | Installation Started | In Progress | Pending | In Progress |  | 1
PRJ298 | River View Business Centre 298 | North Kerala | Kozhikode | Office | 21 | 2026-01-30 | 2026-06-29 | 2026-07-06 | 7 | Mechanical Completion | In Progress | Pending | Delayed |  | 1
PRJ299 | Golden Gate Business Centre 299 | Central Kerala | Idukki | Hotel | 48 | 2026-02-06 | 2026-08-05 | 2026-08-03 | -2 | Testing & Commissioning | In Progress | Pending | Early |  | 1
PRJ300 | Emerald Business Centre 300 | South Kerala | Alappuzha | Commercial | 32 | 2026-02-13 | 2026-09-11 | 2026-09-21 | 10 | Handover | Completed | Completed | Delayed |  | 1
PRJ301 | Tech Park Tower 301 | North Kerala | Kozhikode | Office | 60 | 2026-08-15 | 2026-11-15 | 2026-11-15 | 0 | Handover | Completed | Completed | On Time |  | 1
PRJ302 | Lake View Hospital 302 | Central Kerala | Ernakulam | Hospital | 72 | 2026-08-20 | 2026-12-20 | 2026-12-27 | 7 | Testing & Commissioning | Completed | Completed | Delayed |  | 1
PRJ303 | Green Valley Hotel 303 | South Kerala | Alappuzha | Hotel | 45 | 2026-09-01 | 2026-12-15 |  | -5 | Installation Started | In Progress | Pending | Early |  | 1
PRJ304 | Sunrise Apartments 304 | North Kerala | Wayanad | Residential | 38 | 2026-09-10 | 2027-01-10 |  | 10 | Material Delivered | In Progress | Pending | Delayed |  | 1
PRJ305 | Metro Office Complex 305 | Central Kerala | Thrissur | Commercial | 55 | 2026-09-18 | 2026-12-18 |  | 0 | Material Ordered | In Progress | Pending | On Time |  | 1
1
0
Formulas:
Planned Completion = [Start Date]+CHOOSE(MOD(ROW()-2,5)+1,90,120,150,180,210)
Actual Completion = IF(MOD(ROW()-2,4)=0,"",[Planned Completion]+CHOOSE(MOD(ROW()-2,5)+1,-5,0,7,-2,10))

## Lists
Region | City | Customer Type | Installation Stage | Status | Handover Status
North Kerala | Kochi | Residential | Material Ordered | On Track | Pending
Central Kerala | Trivandrum | Commercial | Material Delivered | Delayed | Completed
South Kerala | Kozhikode | Hospital | Installation Started | In Progress
| Thrissur | Hotel | Installation Completed | Completed
| Kottayam | Apartment | Testing | On Hold
| Kannur | Office | Inspection
| Palakkad | Shopping Mall | Handover
Kollam
Alappuzha
Pathanamthitta
Kasargod
Wayanad

## Pivot
Row Labels | Count of Project ID | Row Labels | Count of Project ID |  | Row Labels | Count of Project ID | Row Labels | Count of Project ID | Row Labels | Count of Project ID | Row Labels | Count of Project ID
Central Kerala | 105 | Handover | 57 |  | Completed | 58 | Completed | 58 | Apartment | 49 | Alappuzha | 26
North Kerala | 100 | Installation Started | 50 |  | In Progress | 247 | Pending | 247 | Commercial | 51 | Idukki | 49
South Kerala | 100 | Material Delivered | 50 |  | Grand Total | 305 | Grand Total | 305 | Hospital | 50 | Kannur | 25
Grand Total | 305 | Material Ordered | 50 | [5 empty] | Hotel | 51 | Kasaragod | 24
|  | Mechanical Completion | 48 | [5 empty] | Office | 51 | Kochi | 5
|  | Testing & Commissioning | 50 | [5 empty] | Residential | 52 | Kollam | 25
|  | Grand Total | 305 | [5 empty] | Shopping Mall | 1 | Kozhikode | 26
[9 empty] | Grand Total | 305 | Pathanamthitta | 24
[11 empty] | Thrissur | 50
[11 empty] | Trivandrum | 25
[11 empty] | Wayanad | 25
[11 empty] | Ernakulam | 1
[11 empty] | Grand Total | 305
Row Labels | Count of Project ID
Delayed | 92
Early | 93 |  | Average of Delay (Days)
In Progress | 75 |  | 1.9739
On Time | 45
Grand Total | 305
Sum of Project Value (₹ Lakhs)
11370
Average of Project Value (₹ Lakhs)
37.2787
|  |  | Row Labels | Sum of Project Value (₹ Lakhs) | Row Labels | Sum of Project Value (₹ Lakhs)
|  |  | Central Kerala | 3992 | Completed | 2265
|  |  | North Kerala | 3709 | In Progress | 9105
|  |  | South Kerala | 3669 | Grand Total | 11370
|  |  | Grand Total | 11370
Row Labels | Sum of Project Value (₹ Lakhs)
Lake View Hospital 302 | 72
Harmony Grand Hotel 064 | 65 |  | Row Labels | Sum of Project Value (₹ Lakhs)
Harmony Residency 164 | 65 |  | Apartment | 1949
Harmony Heights 104 | 65 |  | Commercial | 2002
Harmony Apartments 094 | 65 |  | Hospital | 1754
Harmony Towers 194 | 65 |  | Hotel | 1775
Harmony Apartments 174 | 65 |  | Office | 2046
Harmony Grand Hotel 224 | 65 |  | Residential | 1789
Harmony Apartments 254 | 65 |  | Shopping Mall | 55
Harmony Heights 264 | 65 |  | Grand Total | 11370
Harmony Business Centre 054 | 65
Harmony Towers 034 | 65
Harmony Business Centre 134 | 65
Harmony Enclave 284 | 65
Harmony Business Centre 214 | 65
Harmony Grand Hotel 144 | 65
Harmony Business Centre 294 | 65
Harmony Heights 024 | 65
Harmony Care Hospital 074 | 65
Harmony Heights 184 | 65
Harmony Care Hospital 154 | 65
Harmony Residency 084 | 65
Harmony Care Hospital 234 | 65
Harmony Residency 244 | 65
Harmony Enclave 044 | 65
Harmony Towers 114 | 65
Harmony Enclave 124 | 65
Harmony Apartments 014 | 65
Harmony Towers 274 | 65
Harmony Enclave 204 | 65
Metro Business Park | 65
Tech Park Tower 301 | 60 | Row Labels
Sunrise Grand Hotel 066 | 55 | Completed
Sunrise Residency 166 | 55 | In Progress
Sunrise Heights 106 | 55 | Grand Total
Sunrise Apartments 096 | 55
Sunrise Towers 196 | 55
Sunrise Apartments 176 | 55
Sunrise Grand Hotel 226 | 55
Sunrise Apartments 256 | 55
Sunrise Heights 266 | 55 | Row Labels | Sum of Project Value (₹ Lakhs)
Sunrise Business Centre 056 | 55 | Completed | 2265
Sunrise Towers 036 | 55 | In Progress | 9105
Sunrise Business Centre 136 | 55 | Grand Total | 11370
City Centre Mall | 55
Sunrise Business Centre 216 | 55
Sunrise Grand Hotel 146 | 55
Sunrise Business Centre 296 | 55
Sunrise Heights 026 | 55
Sunrise Care Hospital 076 | 55
Sunrise Heights 186 | 55
Sunrise Care Hospital 156 | 55
Sunrise Residency 086 | 55
Sunrise Care Hospital 236 | 55
Sunrise Residency 246 | 55
Sunrise Enclave 046 | 55
Sunrise Towers 116 | 55
Sunrise Enclave 126 | 55
Sunrise Apartments 016 | 55
Sunrise Towers 276 | 55
Sunrise Enclave 206 | 55
Sunrise Enclave 286 | 55
Metro Office Complex 305 | 55
Golden Gate Care Hospital 239 | 48
Golden Gate Heights 029 | 48
Golden Gate Enclave 289 | 48
Golden Gate Apartments 019 | 48
Golden Gate Residency 089 | 48
Golden Gate Apartments 099 | 48
Golden Gate Enclave 129 | 48
Golden Gate Towers 279 | 48
Golden Gate Grand Hotel 149 | 48
Tech Square Offices | 48
Golden Gate Heights 189 | 48
Golden Gate Towers 199 | 48
Golden Gate Residency 249 | 48
Golden Gate Towers 039 | 48
Golden Gate Enclave 049 | 48
Golden Gate Apartments 179 | 48
Golden Gate Enclave 209 | 48
Golden Gate Apartments 259 | 48
Golden Gate Grand Hotel 069 | 48
Golden Gate Business Centre 059 | 48
Golden Gate Grand Hotel 229 | 48
Golden Gate Business Centre 139 | 48
Golden Gate Heights 109 | 48
Golden Gate Business Centre 219 | 48
Golden Gate Heights 269 | 48
Golden Gate Business Centre 299 | 48
Golden Gate Residency 169 | 48
Golden Gate Care Hospital 079 | 48
Golden Gate Care Hospital 159 | 48
Golden Gate Towers 119 | 48
Green Valley Hotel 303 | 45
Skyline Care Hospital 233 | 42
Skyline Heights 023 | 42
Skyline Enclave 283 | 42
Skyline Towers 033 | 42
Orchid Hospital | 42
Skyline Towers 113 | 42
Skyline Enclave 123 | 42
Skyline Towers 193 | 42
Skyline Grand Hotel 143 | 42
Skyline Towers 273 | 42
Skyline Heights 183 | 42
Skyline Apartments 013 | 42
Skyline Care Hospital 153 | 42
Skyline Apartments 093 | 42
Skyline Enclave 043 | 42
Skyline Apartments 173 | 42
Skyline Enclave 203 | 42
Skyline Apartments 253 | 42
Skyline Grand Hotel 063 | 42
Skyline Business Centre 053 | 42
Skyline Grand Hotel 223 | 42
Skyline Business Centre 133 | 42
Skyline Heights 103 | 42
Skyline Business Centre 213 | 42
Skyline Heights 263 | 42
Skyline Business Centre 293 | 42
Skyline Residency 243 | 42
Skyline Residency 163 | 42
Skyline Residency 083 | 42
Skyline Care Hospital 073 | 42
Lakeside Grand Hotel 065 | 38
Lakeside Residency 165 | 38
Lakeside Heights 105 | 38
Lakeside Apartments 175 | 38
Lakeside Towers 195 | 38
Lakeside Apartments 255 | 38
Lakeside Grand Hotel 225 | 38
Grand Palace Hotel | 38
Lakeside Heights 265 | 38
Lakeside Business Centre 055 | 38
Lakeside Towers 035 | 38
Lakeside Business Centre 135 | 38
Lakeside Apartments 015 | 38
Lakeside Business Centre 215 | 38
Lakeside Grand Hotel 145 | 38
Lakeside Business Centre 295 | 38
Lakeside Heights 025 | 38
Lakeside Care Hospital 075 | 38
Lakeside Heights 185 | 38
Lakeside Care Hospital 155 | 38
Lakeside Residency 085 | 38
Lakeside Care Hospital 235 | 38
Lakeside Residency 245 | 38
Lakeside Enclave 045 | 38
Lakeside Towers 115 | 38
Lakeside Enclave 125 | 38
Lakeside Towers 275 | 38
Lakeside Enclave 205 | 38
Lakeside Apartments 095 | 38
Lakeside Enclave 285 | 38
Sunrise Apartments 304 | 38
Emerald Apartments 260 | 32
Emerald Enclave 050 | 32
Emerald Business Centre 300 | 32
Emerald Grand Hotel 070 | 32
Emerald Enclave 210 | 32
Emerald Grand Hotel 150 | 32
Emerald Business Centre 140 | 32
Emerald Grand Hotel 230 | 32
Emerald Care Hospital 160 | 32
Emerald Heights 030 | 32
Emerald Apartments 100 | 32
Emerald Heights 110 | 32
Emerald Towers 280 | 32
Emerald Heights 190 | 32
Emerald Business Centre 060 | 32
Emerald Heights 270 | 32
Emerald Business Centre 220 | 32
Emerald Residency 090 | 32
Emerald Care Hospital 080 | 32
Emerald Residency 170 | 32
Emerald Care Hospital 240 | 32
Emerald Residency 250 | 32
Emerald Enclave 130 | 32
Emerald Towers 040 | 32
Sunrise Towers | 32
Emerald Towers 120 | 32
Emerald Enclave 290 | 32
Emerald Towers 200 | 32
Emerald Apartments 180 | 32
Emerald Apartments 020 | 32
Silver Oak Heights 267 | 27
Silver Oak Apartments 177 | 27
Silver Oak Towers 037 | 27
Silver Oak Business Centre 297 | 27
Silver Oak Business Centre 217 | 27
Silver Oak Care Hospital 077 | 27
Silver Oak Residency 167 | 27
Silver Oak Care Hospital 157 | 27
Silver Oak Towers 197 | 27
Silver Oak Care Hospital 237 | 27
Silver Oak Business Centre 057 | 27
Silver Oak Enclave 047 | 27
Silver Oak Heights 187 | 27
Harmony Heights | 27
Silver Oak Residency 087 | 27
Silver Oak Apartments 097 | 27
Silver Oak Residency 247 | 27
Silver Oak Enclave 287 | 27
Silver Oak Towers 117 | 27
Silver Oak Grand Hotel 067 | 27
Silver Oak Towers 277 | 27
Silver Oak Grand Hotel 147 | 27
Silver Oak Apartments 257 | 27
Silver Oak Grand Hotel 227 | 27
Silver Oak Business Centre 137 | 27
Silver Oak Heights 027 | 27
Silver Oak Heights 107 | 27
Silver Oak Enclave 127 | 27
Silver Oak Enclave 207 | 27
Silver Oak Apartments 017 | 27
Royal Palm Residency 082 | 24
Royal Palm Apartments 172 | 24
Royal Palm Towers 112 | 24
Royal Palm Care Hospital 072 | 24
Royal Palm Business Centre 132 | 24
Royal Palm Care Hospital 152 | 24
Royal Palm Residency 242 | 24
Royal Palm Care Hospital 232 | 24
Royal Palm Towers 272 | 24
Royal Palm Enclave 042 | 24
Green Valley Apartments | 24
Royal Palm Enclave 122 | 24
Royal Palm Business Centre 292 | 24
Royal Palm Enclave 202 | 24
Royal Palm Residency 162 | 24
Royal Palm Enclave 282 | 24
Royal Palm Towers 032 | 24
Royal Palm Apartments 012 | 24
Royal Palm Towers 192 | 24
Royal Palm Grand Hotel 142 | 24
Royal Palm Apartments 092 | 24
Royal Palm Grand Hotel 222 | 24
Royal Palm Apartments 252 | 24
Royal Palm Heights 022 | 24
Royal Palm Business Centre 052 | 24
Royal Palm Heights 102 | 24
Royal Palm Business Centre 212 | 24
Royal Palm Heights 182 | 24
Royal Palm Heights 262 | 24
Royal Palm Grand Hotel 062 | 24
River View Towers 038 | 21
River View Business Centre 218 | 21
River View Apartments 178 | 21
River View Enclave 128 | 21
River View Care Hospital 238 | 21
River View Enclave 208 | 21
River View Towers 198 | 21
River View Apartments 018 | 21
River View Business Centre 058 | 21
River View Grand Hotel 068 | 21
River View Care Hospital 078 | 21
River View Grand Hotel 148 | 21
River View Residency 248 | 21
River View Grand Hotel 228 | 21
River View Towers 118 | 21
River View Heights 028 | 21
River View Towers 278 | 21
River View Heights 108 | 21
River View Apartments 258 | 21
River View Heights 188 | 21
River View Business Centre 138 | 21
River View Heights 268 | 21
River View Business Centre 298 | 21
River View Residency | 21
River View Care Hospital 158 | 21
River View Residency 088 | 21
River View Enclave 048 | 21
River View Residency 168 | 21
River View Enclave 288 | 21
River View Apartments 098 | 21
Green Valley Towers 031 | 18
Green Valley Apartments 251 | 18
Green Valley Towers 271 | 18
Green Valley Enclave 041 | 18
Green Valley Business Centre 291 | 18
Green Valley Enclave 121 | 18
Green Valley Towers 111 | 18
Green Valley Enclave 201 | 18
Green Valley Apartments 091 | 18
Green Valley Enclave 281 | 18
Green Valley Business Centre 131 | 18
Green Valley Grand Hotel 061 | 18
Green Valley Care Hospital 151 | 18
Green Valley Grand Hotel 141 | 18
Skyline Residency | 18
Green Valley Grand Hotel 221 | 18
Green Valley Towers 191 | 18
Green Valley Heights 021 | 18
Green Valley Apartments 011 | 18
Green Valley Heights 101 | 18
Green Valley Apartments 171 | 18
Green Valley Heights 181 | 18
Green Valley Business Centre 051 | 18
Green Valley Heights 261 | 18
Green Valley Business Centre 211 | 18
Green Valley Residency 081 | 18
Green Valley Care Hospital 071 | 18
Green Valley Residency 161 | 18
Green Valley Care Hospital 231 | 18
Green Valley Residency 241 | 18
Grand Total | 11370

## Dashboard
PROJECT MONITORING DASHBOARD
TOTAL PROJECTS |  |  |  | COMPLETED |  | IN PROGRESS | HANDOVERS | DELAYED PROJECTS | ON-TIME COMPLETION | AVERAGE DELAY | TOTAL PROJECT VALUE | AVERAGE PROJECT VALUE
305 |  |  |  | 58 |  | 247 | 58 | 92 | 45 | 1.9739 | 11370 | 37.2787
HIGHEST VALUE PROJECT ANALYSIS
Highest Project Value : ₹65 Lakhs
Highest Value Projects : Multiple
Region | Status | Customer Type
North Kerala | Completed | Hospital
Central Kerala | In Progress | Office
North Kerala | Completed | Hotel
South Kerala | Completed | Hospital
North Kerala | In Progress | Apartment
2 | Answer | Countifs | North Kerala- Completed projects
1 | Answer | Countifs | Completed projects are there in North Kerala for the Hospital customer type
Region | Status | Project Value
North Kerala | Completed | 50
North Kerala | In Progress | 65 |  | 48.3333 | Averageif
South Kerala | Completed | 40 |  | 52.5 | Averageifs
North Kerala | Completed | 55 |  | 40 | Averageifs
105 | Sumifs | total Project Value of Completed projects in North Kerala
170 | Sumifs | total Project Value of projects in North Kerala, regardless of Status
145 | Sumif
Region | Project Value
North Kerala | 50
North Kerala | 65
South Kerala | 40
North Kerala | 55
56.6667 | Averageif
0 | iferror
Project Value | Number of Projects
100 | 5
200 | 0 | 0 | IFERROR
Project ID | Project Name | Project Value
PRJ001 | Kochi Heights | 50
PRJ002 | Metro Tower | 65
PRJ003 | City Hospital | 40
| City Hospital | VLOKKUP
| 65 | VLOKKUP
#N/A
Not Found
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.